## Ark1
Lofthus frukt og saft | WEEK 1: PLANNING |  |  |  |  | WEEK 2: DESIGN |  |  |  |  | WEEK 3: BUILD |  |  |  |  | WEEK 4: FINISH/LAUNCH
| Mon 26 Nov | Tue 27 Nov | Wed 28 Nov | Thu 29 Nov | Fri 20 Nov | Mon 3 Dec | Tue 4 Dec | Wed 5 Dec | Thu 6 Dec | Fri 7 Dec | Mon 10 Dec | Tue 11 Dec | Wed 12 Dec | Thu 13 Dec | Fri 14 Dec | Mon 17 Dec | Tue 18 Dec | Wed 19 Dec | Thu 20 Dec | Fri 21 Dec
PROJECT MANAGER | PROJECT MANAGEMENT(keeping customer updated) |  |  |  |  | PROJECT MANAGEMENT(keeping customer updated) |  |  |  |  | PROJECT MANAGEMENT(keeping customer updated) |  |  |  |  | PROJECT MANAGEMENT(keeping customer updated)
PROJECT MANAGER CONTENT DEVELOPER DESIGNER FRONT END DEVELOPER | START: Init/Customer meeting
PROJECT MANAGER CONTENT DEVELOPER DESIGNER | PLAN PROJECT
CONTENT DEVELOPER DESIGNER |  | RESEARCH
CONTENT DEVELOPER DESIGNER |  |  | PLAN CONTENT
CONTENT DEVELOPER DESIGNER FRONT END DEVELOPER |  |  |  |  | OUTLINE OF SITE | STRUCTURE OF SITE
DESIGNER | [7 empty] | STYLETILE/MOODBOARD |  |  | WIREFRAMES
CONTENT DEVELOPER | [7 empty] | DEVELOP TEXT CONTENT
PHOTOGRAPHER DESIGNER | [7 empty] | PHOTOS: Products |  |  | PHOTOS: Employees
CONTENT DEVELOPER DESIGNER | [11 empty] | PLANNING AND TESTING UX/UI |  |  |  | TESTING UX/UI
FRONT END DEVELOPER | [10 empty] | BUILD SITE (Html & CSS) |  |  |  |  | BUILD SITE(Html & CSS)
FRONT END DEVELOPER | [16 empty] | TEST ON DIFFERENT BROWSERS AND PLATFORMS
FRONT END DEVELOPER | [16 empty] | VALIDATE
CONTENT DEVELOPER DESIGNER FRONT END DEVELOPER | [17 empty] | ADJUSTMENTS
PROJECT MANAGER CONTEND DEVELOPER DESIGNER FRONT END DEVELOPER | [19 empty] | LAST MEETING/WEBSITE LAUNCH